## Version History
Clarion Coach - Version History & Document Control
Project: AI-Powered Real-Time Customer Support Coaching Assistant ¦ Author: Sangaraju Suvida ¦ Internship: Infosys Springboard ¦ Architecture: Code-Based Multi-Agent System ¦ Stack: React + TypeScript + Vite + FastAPI + Google Gemini + ChromaDB / RAG
Version History & Document Control
Version | Date | Author | Change Description | Status | Reviewed By | Approved By
v0.1 | 2026-07-15 | Sangaraju Suvida | Initial project creation - React/Vite frontend, FastAPI backend, project configuration, Pydantic schemas, API structure and session configuration. | Completed | Self | -
v0.2 | 2026-07-20 | Sangaraju Suvida | Core AI architecture implemented - code-based Orchestrator, Customer Simulator Agent, Intent Analysis Agent, Knowledge Recommendation Agent, Coaching Agent and Escalation Monitor Agent with structured Pydantic outputs. | Completed | Peer Review | -
v0.3 | 2026-07-28 | Sangaraju Suvida | RAG pipeline implemented - knowledge-document processing, text chunking, Sentence Transformer embeddings, ChromaDB vector storage, semantic similarity retrieval and knowledge recommendations. | In Review | QA Team | -
v0.4 | 2026-08-05 | Sangaraju Suvida | Coaching interface and interaction modes completed - Simulator Mode, Manual Mode, Replay Mode, conversation history, coaching scores, communication evaluation, escalation-risk analysis and agent execution trace. | In Review | Mentor | Yahavarshini
v0.5 | 2026-08-12 | Sangaraju Suvida | Dynamic conversation improvements completed - previous suggestions and coaching tips passed as context, multi-turn response variation, session-aware coaching and context-grounded response generation. | Testing | Mentor | -
v0.6 | 2026-08-18 | Sangaraju Suvida | Response-quality hardening completed - prevention of invented customer names, order/transaction IDs and unsupported completed actions; logged-in agent-name flow integrated; frontend API timeout and error handling improved. | Completed | Self | Yahavarshini
v1.0 | 2026-08-28 | Sangaraju Suvida | Final project completion - Gemini and ChromaDB integration, security cleanup, testing, reporting/PDF functionality, detailed project documentation, Agile/Defect/Unit Test documentation and final submission preparation. | Submitted | Yahavarshini | Yahavarshini

## Product Backlog
Clario Coach - Product Backlog (AI-Powered Real-Time Customer Support Coaching Assistant - Sangaraju Suvida)
Project: AI-Powered Real-Time Customer Support Coaching Assistant ¦ Architecture: Code-Based Multi-Agent System ¦ Stack: React + TypeScript + Vite + FastAPI + Google Gemini + ChromaDB / RAG ¦ Milestones: 4
Planned Sprint | Actual Sprint | US ID | User Story / Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US-001 | As a user, I want the React/Vite frontend and FastAPI backend set up so the application can run and communicate end-to-end. | MUST HAVE | No Dependency | Sangaraju Suvida | 3- Completed
1 | 1 | US-002 | As a system, I want a code-based Orchestrator to coordinate specialized AI agents and manage the conversation workflow. | MUST HAVE | US-001 | Sangaraju Suvida | 3- Completed
1 | 1 | US-003 | As a developer, I want Pydantic request and response models so agent outputs and API data remain structured and validated. | MUST HAVE | US-002 | Sangaraju Suvida | 3- Completed
2 | 2 | US-004 | As a trainee, I want customer intent, sentiment, frustration, urgency and confidence analysed for each customer message. | MUST HAVE | US-002, Gemini API | Sangaraju Suvida | 3- Completed
2 | 2 | US-005 | As a trainee, I want knowledge documents processed, embedded and stored so relevant support information can be retrieved semantically. | MUST HAVE | US-001, ChromaDB, Sentence Transformers | Sangaraju Suvida | 3- Completed
2 | 2 | US-006 | As a trainee, I want the Knowledge Agent to retrieve relevant knowledge from ChromaDB and provide grounded context for coaching. | MUST HAVE | US-004, US-005 | Sangaraju Suvida | 3- Completed
3 | 3 | US-007 | As a trainee, I want the Coaching Agent to generate concise customer-ready response suggestions using conversation context and retrieved knowledge. | MUST HAVE | US-004, US-006 | Sangaraju Suvida | 3- Completed
3 | 3 | US-008 | As a trainee, I want coaching feedback on tone, clarity, grammar, professionalism and empathy with an overall coaching score. | MUST HAVE | US-007 | Sangaraju Suvida | 3- Completed
3 | 3 | US-009 | As a trainee, I want escalation risk evaluated with probability, risk level, reasoning and a recommended action. | MUST HAVE | US-004, conversation history | Sangaraju Suvida | 3- Completed
3 | 3 | US-010 | As a trainee, I want Simulator Mode to generate realistic multi-turn customer replies using persona, scenario and emotional progression. | MUST HAVE | US-002, US-004 | Sangaraju Suvida | 3- Completed
4 | 4 | US-011 | As a trainee, I want Manual Mode to submit customer messages through the Intent, Knowledge, Coaching and Escalation pipeline. | MUST HAVE | US-004, US-006, US-007, US-009 | Sangaraju Suvida | 3- Completed
4 | 4 | US-012 | As a trainee, I want Replay Mode to process transcript conversations turn by turn for analysis and coaching. | MUST HAVE | US-007, transcript handling | Sangaraju Suvida | 3- Completed
4 | 4 | US-013 | As a user, I want dynamic responses that remember prior turns and prevent invented customer names, order IDs and unsupported completed actions. | MUST HAVE | US-007, session history, validation | Sangaraju Suvida | 3- Completed
4 | 4 | US-014 | As a user, I want the signed-in support representative name, API error handling, reporting and security checks integrated for project completion. | SHOULD HAVE | US-011, US-012 | Sangaraju Suvida | 3- Completed

## Sprint Backlog
Clario Coach - Sprint Backlog (Four-Milestone Task Breakdown)
Task-level decomposition with owner, effort, dependencies and completion status ¦ Assignee: Sangaraju Suvida
Sprint | Task ID | US ID | Task / Activity | Assignee | Est. Hrs | Actual Hrs | Dependency | Status
1 | T-01 | US-001 | Set up React/Vite frontend, FastAPI backend, project configuration and environment structure. | Sangaraju Suvida | 6 | 6 | - | 3- Completed
1 | T-02 | US-002 | Implement the code-based Orchestrator and define the application-level agent workflow. | Sangaraju Suvida | 8 | 8 | T-01 | 3- Completed
1 | T-03 | US-003 | Create Pydantic request/response schemas and connect the /chat data contract. | Sangaraju Suvida | 5 | 5 | T-02 | 3- Completed
2 | T-04 | US-004 | Implement Intent Analysis for intent, sentiment, frustration, urgency and confidence. | Sangaraju Suvida | 8 | 8 | T-03 | 3- Completed
2 | T-05 | US-005 | Implement document ingestion, chunking, embeddings and ChromaDB storage. | Sangaraju Suvida | 10 | 10 | T-03 | 3- Completed
2 | T-06 | US-006 | Implement Knowledge Recommendation and semantic retrieval for relevant support context. | Sangaraju Suvida | 7 | 7 | T-05 | 3- Completed
3 | T-07 | US-007 | Implement Coaching Agent with dynamic customer-ready response generation. | Sangaraju Suvida | 10 | 10 | T-04,T-06 | 3- Completed
3 | T-08 | US-008 | Implement coaching evaluation for tone, clarity, grammar, professionalism and empathy. | Sangaraju Suvida | 8 | 8 | T-07 | 3- Completed
3 | T-09 | US-009 | Implement Escalation Monitor with risk probability, level, reasoning and recommended action. | Sangaraju Suvida | 7 | 7 | T-04 | 3- Completed
3 | T-10 | US-010 | Implement Simulator Mode with persona, scenario, conversation history and multi-turn context. | Sangaraju Suvida | 9 | 9 | T-02,T-04 | 3- Completed
4 | T-11 | US-011 | Implement Manual Mode using the common Intent, Knowledge, Coaching and Escalation pipeline. | Sangaraju Suvida | 5 | 5 | T-07,T-09 | 3- Completed
4 | T-12 | US-012 | Implement Replay Mode for transcript-based turn-by-turn analysis and coaching. | Sangaraju Suvida | 6 | 6 | T-07 | 3- Completed
4 | T-13 | US-013 | Add previous-suggestion memory, anti-hallucination controls and unsupported-action prevention. | Sangaraju Suvida | 9 | 9 | T-07,T-10 | 3- Completed

## Stand up Meeting
Clario Coach - Daily Stand-up Log (Four Milestones)
Individual project log: Yesterday / Today / Blockers / Action Items ¦ Team Member: Sangaraju Suvida
Date | Sprint | Team Member | What was done yesterday? | What will be done today? | Blockers / Impediments | Action Items
2026-07-15 | Milestone 1 | Sangaraju Suvida | Established frontend, backend, API structure and project foundation. | Implement Orchestrator and structured data flow. | None | Complete core orchestration flow
2026-07-18 | Milestone 1 | Sangaraju Suvida | Implemented Orchestrator and Pydantic contracts. | Build Intent Analysis and emotional-signal analysis. | None | Validate structured intent output
2026-07-22 | Milestone 2 | Sangaraju Suvida | Implemented intent and sentiment analysis. | Build RAG ingestion, embeddings and ChromaDB retrieval. | Dependency setup | Complete knowledge retrieval
2026-07-25 | Milestone 2 | Sangaraju Suvida | Completed RAG pipeline and knowledge retrieval. | Integrate retrieved knowledge into Coaching Agent. | None | Validate grounded coaching
2026-07-28 | Milestone 3 | Sangaraju Suvida | Built Coaching Agent and communication scoring. | Implement Escalation Monitor and Simulator Mode. | None | Complete multi-turn training flow
2026-08-02 | Milestone 3 | Sangaraju Suvida | Completed coaching, escalation and simulator workflow. | Add Manual and Replay modes with session context. | None | Validate interaction modes
2026-08-07 | Milestone 4 | Sangaraju Suvida | Implemented dynamic responses and response-safety controls. | Complete agent identity flow, API handling and reporting. | None | Run final integration checks
2026-08-18 | Milestone 4 | Sangaraju Suvida | Completed testing, documentation and project artefacts. | Prepare final submission package. | None | Final review and submission

## Retrospection
Clario Coach - Milestone Retrospectives
What went well / What went wrong / Improvements ¦ Owner: Sangaraju Suvida
Sprint (Dates) | What Went Well | What Went Wrong / Challenges | Action Items / Improvements | Owner | Due Date / Status
Milestone 1(15-20 Jul 2026) | Frontend/backend foundation and structured orchestration were established. | Environment and integration setup required alignment between frontend and backend configuration. | Stabilize local setup and keep API/data contracts documented. | Sangaraju Suvida | Completed
Milestone 2(22-27 Jul 2026) | Intent analysis and ChromaDB/RAG retrieval established the core AI and knowledge pipeline. | Knowledge retrieval needed strong grounding to avoid unsupported facts. | Strengthen retrieval context and grounding rules before coaching. | Sangaraju Suvida | Completed
Milestone 3(28 Jul-05 Aug) | Coaching, escalation and Simulator Mode enabled realistic support training. | Early multi-turn output could become repetitive or generic. | Use conversation history, prior suggestions and coaching context. | Sangaraju Suvida | Completed
Milestone 4(05-18 Aug) | Dynamic responses, safety controls, API handling, reporting and documentation were finalized. | Final integration required careful checking of names, identifiers and unsupported action claims. | Keep final validation focused on safety, integration, security and submission readiness. | Sangaraju Suvida | Completed