## Defect Tracker
Clarion Coach - Defect Tracker
Project: AI-Powered Real-Time Customer Support Coaching Assistant ¦ Author: Sangaraju Suvida ¦ Internship: Infosys Springboard ¦ Architecture: Code-Based Multi-Agent System ¦ Stack: React + TypeScript + Vite + FastAPI + Google Gemini + ChromaDB / RAG ¦ Milestones: 4
Defect Log & Resolution History
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Sangaraju Suvida | 2026-07-28 | Local backend setup initially failed because the pinned NumPy dependency was incompatible with the available Python environment. | Milestone 1 | Sangaraju Suvida | Environment / Compatibility | Configured a compatible virtual environment and aligned the backend dependency installation with the project requirements. | 2026-07-28 | Closed | Backend environment was stabilized for local execution.
2 | Sangaraju Suvida | 2026-07-30 | Frontend chat requests needed a clear connection to the FastAPI backend instead of relying on demo behaviour. | Milestone 1 | Sangaraju Suvida | Integration | Configured the frontend API base URL so real API mode routes requests to the FastAPI backend. | 2026-07-30 | Closed | Real backend and demo/mock modes are clearly separated.
3 | Sangaraju Suvida | 2026-08-02 | The Orchestrator needed a structured way to pass analysis results between specialized agents. | Milestone 1 | Sangaraju Suvida | Architecture / Functional | Used Python function calls and Pydantic models to pass structured outputs between agents and aggregate the final response. | 2026-08-02 | Closed | Code-based orchestration is now consistent across the pipeline.
4 | Sangaraju Suvida | 2026-08-04 | Customer intent, sentiment, frustration and urgency required consistent structured output for downstream coaching. | Milestone 2 | Sangaraju Suvida | AI / Functional | Implemented structured IntentAnalysis output with intent, sentiment, frustration, urgency, confidence and satisfaction trend. | 2026-08-04 | Closed | Structured analysis is available to subsequent agents.
5 | Sangaraju Suvida | 2026-08-05 | Knowledge retrieval required relevant context from uploaded support documents rather than relying only on model-generated information. | Milestone 2 | Sangaraju Suvida | AI / RAG | Implemented document processing, embeddings, semantic retrieval and ChromaDB-backed knowledge recommendations. | 2026-08-05 | Closed | Relevant knowledge is supplied to the coaching workflow.
6 | Sangaraju Suvida | 2026-08-07 | Retrieved knowledge or missing knowledge could lead to unsupported policy claims if grounding rules were not enforced. | Milestone 2 | Sangaraju Suvida | AI / RAG | Strengthened grounding rules so unsupported policies are not presented as facts and irrelevant retrieval is not treated as authoritative. | 2026-08-07 | Closed | Knowledge-grounded behaviour retained in the final coaching prompt.
7 | Sangaraju Suvida | 2026-08-10 | AI-generated coaching responses could repeat the same wording across multiple conversation turns. | Milestone 3 | Sangaraju Suvida | AI / Functional | Passed previous suggestions and coaching tips into the coaching context and added dynamic response rules. | 2026-08-10 | Closed | Five-turn browser validation showed varied coaching drafts.
8 | Sangaraju Suvida | 2026-08-12 | Generated customer-facing drafts could contain invented customer names that were not supplied by the conversation. | Milestone 3 | Sangaraju Suvida | AI / Functional | Added strict customer-name grounding rules and response validation. | 2026-08-12 | Closed | No invented customer names were observed in the verified simulator flow.
9 | Sangaraju Suvida | 2026-08-13 | Generated customer-facing drafts could contain fabricated order or transaction identifiers. | Milestone 3 | Sangaraju Suvida | AI / Functional | Added identifier grounding rules and validation; only identifiers actually present in context may be reused. | 2026-08-13 | Closed | Real customer-provided identifiers remain usable.
10 | Sangaraju Suvida | 2026-08-15 | Coaching drafts could incorrectly claim that a refund, reset, dispatch or other action had already been completed. | Milestone 4 | Sangaraju Suvida | AI / Safety / Functional | Updated prompt rules to provide a supported next step unless the application has actually confirmed the action. | 2026-08-15 | Closed | Unsupported completed-action claims were removed from verified drafts.
11 | Sangaraju Suvida | 2026-08-15 | The signed-in support representative name needed to reach the Coaching Agent without being confused with customer identity. | Milestone 4 | Sangaraju Suvida | Integration / Identity | Plumbed agent_name from the signed-in user through the frontend API, ChatRequest, Orchestrator and Coaching Agent. | 2026-08-15 | Closed | Agent name is kept separate from customer name and is not inserted into the customer draft.
12 | Sangaraju Suvida | 2026-08-17 | Frontend API failures needed clearer handling instead of appearing as successful requests or silent fallback behaviour. | Milestone 4 | Sangaraju Suvida | Integration / Error Handling | Added request timeout handling and explicit messages for unreachable backend, non-2xx responses and invalid JSON. | 2026-08-17 | Closed | Real API mode now surfaces backend errors clearly.
13 | Sangaraju Suvida | 2026-08-18 | Knowledge upload errors could be interpreted incorrectly when the backend returned a non-success response. | Milestone 4 | Sangaraju Suvida | Integration | Updated knowledgeUpload handling to throw on non-2xx responses instead of treating the error response as valid data. | 2026-08-18 | Closed | Upload failure handling is explicit.
14 | Sangaraju Suvida | 2026-08-18 | Project secrets and generated local data needed to be excluded from version control. | Milestone 4 | Sangaraju Suvida | Security / Configuration | Updated Git ignore rules for environment files, ChromaDB storage and Python cache directories; kept Gemini credentials backend-only. | 2026-08-18 | Closed | No hardcoded API key was identified in the frontend.
15 | Sangaraju Suvida | 2026-06-20 | Long-running or failing API calls needed to fail gracefully without breaking the frontend experience. | Milestone 4 | Sangaraju Suvida | Performance / Reliability | Added a 60-second request timeout and clear failure messages in the frontend API layer. | 2026-08-20 | Closed | Frontend type-check remained clean after the change.
16 | Sangaraju Suvida | 2026-08-28 | Final documentation and project artefacts needed to be complete and traceable for Infosys Springboard submission. | Milestone 4 | Sangaraju Suvida | Documentation | Completed technical documentation, version history, Agile, Defect Tracker and Unit Test Plan artefacts. | 2026-08-28 | Closed | Documentation package prepared for final submission.
Summary: 16 project defects documented across four milestones — Milestone 1: 3 ¦ Milestone 2: 3 ¦ Milestone 3: 3 ¦ Milestone 4: 7 ¦ All items recorded as Closed.